## Task Board and Burnup chart
Task Board
To do |  |  |  | In progress | Done
Create Account |  |  |  | View Offers | Contact method
View Menu |  |  |  | Reset Password | Access my location
view order |  |  |  | Search Restaurants
Search Restaurants
Payment method
Contact method
| Days | 5
| Tasks | 17
| Day | Expected | Done
| 1 | 2 | 2
| 2 | 5 | 6
| 3 | 7 | 5
| 4 | 10 | 8
| 5 | 13 | 14